PROJECT BLUEPRINT

AI-Powered Resume-to-Career

Job Discovery & Career Path Platform

4-Hour Hackathon Edition — No Auth, No DB, Ship Fast

Stack: React + Python (FastAPI)

Integrations: Exa · ElevenLabs · Wispr Flow · Render — all implemented

Team Size: 4 Members

Version 3.0 — All Integrations Core

# Table of Contents

1. Project Overview — Hackathon Scope

2. What We Are Cutting (and Why)

3. Complete User Flow

4. Feature List (Build vs Skip)

5. Recommended Technology Stack

6. Third-Party Integrations — Kaise Use Karenge

7. Simplified System Architecture

8. Team Structure & Responsibilities

9. Career Path — Exa-Driven Generation Strategy

10. Fast Git Workflow (Hackathon Mode)

11. 4-Hour Timeline

12. Demo & Stretch Goals

# 1. Project Overview — Hackathon Scope

Yeh sirf 4 GHANTE ka hackathon hai, isliye yeh document poore product ka plan nahi hai — yeh sirf wahi banayenge jo 4 hours me realistically demo-ready ho sake. Auth, database aur deployment jaisi cheezein jaanbujhkar drop ki gayi hain taaki poora time core AI flow (resume → job → skill gap → career path) pe lage.

## 1.1 Hackathon Goal

Ek working demo dikhana jisme: resume upload ho, real job search ho (Exa), skill gap dikhe, aur ek career roadmap generate ho — end to end, bina kisi login/signup ke.

## 1.2 Golden Rule

‘Simple but working’ > ‘Complex but broken’. Jahan bhi do options ho — ek fast/hardcoded aur ek proper/dynamic — hackathon me hamesha fast wala choose karo.

# 2. What We Are Cutting (and Why)

Is version me Exa, ElevenLabs, Wispr Flow aur Render — chaaron hi core build me shamil hain (koi stretch goal nahi). Isliye time-budget tight hai, aur neeche di gayi cheezein poori tarah cut karni hongi taaki in char integrations ke liye time bache.

| Cutting | Why | Instead |
| --- | --- | --- |
| Authentication (login/signup/JWT) | Setup + testing me 45–60 min lag sakte hain — 4 integrations (Exa/ElevenLabs/Wispr/Render) ke saamne priority nahi hai. | No login. App directly khulte hi resume upload screen dikhe. |
| Persistent Database (PostgreSQL) | Schema design + ORM setup + migrations time khaate hain, aur Render ka managed DB setup bhi extra time lega. | Data sirf request/response me rahega; frontend apne state (React state) me sab kuch hold karega. |
| Progress tracking dashboard | UI ke liye extra time, core flow ke liye zaroori nahi. | Skip — agar bahut time bache to hi last me add karo. |
| NLP-based skill extraction (spaCy) | Model load + setup time. | Simple predefined skills keyword-list se match (Python set intersection). |
| Separate /job/{id} DB lookup | Extra endpoint + storage ki zarurat. | Job search API call hi listing + full detail dono ek saath de de; frontend state me poora object already hoga. |

# 3. Complete User Flow

Yeh application step-by-step is order me kaam karegi (no login, seedha use):

- User app khole — seedha resume upload screen (PDF/DOCX).

- System resume parse karke skills, experience, education extract karega (keyword match).

- User apna preferred job title enter karega.

- System Exa API ke through us job title se related real jobs search karega — isi call me full detail bhi le lega.

- Job listing screen par results dikhenge (title, company, location, short snippet).

- User kisi job card pe click karega → uski full detail (already frontend state me hai) instantly dikhegi, koi extra API call nahi.

- System resume ke skills ko us job ki required skills ke saath compare karega aur missing skills dikhayega.

- System usi job title ke liye Exa API se career-path search karega aur result ko structured roadmap (stages + skills) me convert karega.

- User apni preferred technology select karega (dropdown — React/Python/Java/etc.).

- System roadmap ke relevant step ko us technology ke hisab se customize karega (Exa ka doosra targeted search: ‘<tech> roadmap for <job title>’).

- Top 2–3 missing skills ke liye Exa se research links fetch honge.

- ElevenLabs se career roadmap ko voice me sunaya ja sakta hai (Play button).

- Job title / search field me Wispr Flow se seedha bol kar bhi type kiya ja sakta hai.

# 4. Feature List (Build vs Skip)

## 4.1 Complete Feature Table

| Feature | Description | Type |
| --- | --- | --- |
| Resume Upload & Parsing | User PDF/DOCX resume upload karta hai; backend text extract karke skills, experience, education ko structured JSON me convert karta hai. | Core |
| Preferred Job Title Input | Text box (+ optional voice input via Wispr Flow) jaha user apna target job title enter karta hai. | Core |
| AI Job Search | Exa API se real-time web se us job title se related job postings search kiye jaate hain. | Core |
| Job Listing Page | Search results ek card-based list me dikhaye jaate hain — title, company, location, posted date. | Core |
| Job Detail Page | Card click karne par full job description, requirements, responsibilities aur apply link ek dedicated page par khulta hai. | Core |
| Skill Gap Analysis | Resume ke skills aur job ki required skills compare hoke ‘Missing Skills’ list generate hoti hai. | Core |
| Career Path Generator | Job title ke basis par ek structured, stage-wise career roadmap (Beginner → Intermediate → Advanced) banta hai. | Core |
| Technology Preference Input | User se poocha jaata hai ki career path ke liye kaunsi technologies prefer karta hai. | Core |
| Personalized Career Path | Selected technology ke hisab se roadmap customize hokar detailed steps, projects aur tools ke saath diya jaata hai. | Core |
| Research Links for Missing Skills | Har missing skill ke liye Exa API se best documentation, courses aur tutorials ke links fetch hote hain. | Core |
| Voice Narration (ElevenLabs) | Job details ya career roadmap ko natural AI voice me sunne ka option. | Enhancement |
| Voice Input (Wispr Flow) | Job title, search query ya notes ko bolke type karne ki facility (dictation). | Enhancement |
| Save / Download Roadmap | Career path ko PDF ya note ke roop me save/download karna. | Enhancement |
| Progress Dashboard | User apni career path ke stages complete karke track kar sake. | Enhancement |

## 4.2 BUILD — 4-hour hackathon scope (all integrations are core)

- Resume Upload & Parsing (keyword-based, no NLP model)

- Preferred Job Title Input (+ Wispr Flow voice input on this field)

- AI-powered Job Search (Exa) — returns listing + full detail together

- Job Listing + Job Detail (from frontend state, no extra API call)

- Skill Gap Analysis (missing skills)

- Career Path via Exa — dynamic search-based roadmap generation (see Section 9)

- Technology Preference → Exa re-query to customize the roadmap

- Research Links for top 2–3 missing skills (Exa)

- ElevenLabs voice narration of the career roadmap

- Wispr Flow voice input on job-title/search field

- Render deployment — live link for the demo

## 4.3 SKIP entirely for this hackathon

- Authentication / login / signup / JWT

- Persistent database (PostgreSQL/Mongo)

- Progress tracking dashboard

- Email/notification alerts

- NLP-based skill extraction (spaCy/LLM)

## 4.4 Stretch — only if everything above is done with time left

- Downloadable PDF of the roadmap

- Better UI polish / animations

# 5. Recommended Technology Stack

Aapki preference — React (frontend) aur Python (backend) — ke saath, aur Exa, ElevenLabs, Wispr Flow aur Render — chaaron ko core build me integrate karte hue, neeche stack diya gaya hai:

| Layer | Technology | Why |
| --- | --- | --- |
| Frontend | React.js (Vite) | Fast build, component-based, aapki preference ke mutabik. |
| Styling | Tailwind CSS | Rapid, consistent UI styling; React ke saath best combo, no design time waste. |
| Frontend State | Plain React useState/useContext | Sab data (resume, jobs, selected job, roadmap) yahin hold hoga — no DB needed. |
| Backend | Python — FastAPI | Async, auto Swagger docs, React ke saath REST integration me sabse fast aur clean; Exa/ElevenLabs jaise external calls ke liye async zaroori hai. |
| Resume Parsing | pdfplumber / python-docx + keyword match | Resume se text nikaal kar ek predefined skills list ke against match karna — NLP model load nahi karna, time bachega. |
| Data Storage | None (in-memory, request/response only) | 4-hour scope me DB skip — sab kuch ek request cycle me hi process hoga. |
| Job Search + Career Path | Exa API | Job listings, career-path roadmap search, aur research links — teeno ke liye same Exa service reuse hoga. |
| Voice Output | ElevenLabs API | Career roadmap ko natural AI voice me sunana — core feature. |
| Voice Input | Wispr Flow | Job title/search field pe dictation — core feature, koi backend code nahi chahiye. |
| Deployment | Render | Frontend Static Site + Backend Web Service — core deliverable, timeline me hi allocate kiya gaya hai (Section 11). |
| Version Control | Git + GitHub | Team collaboration, lightweight branching (see Section 10). |

## 5.1 Why No Database (even with 4 integrations)

- 4 ghante me schema design + ORM + migrations ka time in 4 integrations ke saamne afford nahi hota.

- Resume upload → turant parse → response me skills bhej do; frontend usko state me rakh le aur baad ke calls (job search, gap analysis, career path) me wahi data body me bhej de.

- Stateless backend deploy karna (Render par) bhi aasan hota hai — koi DB provisioning/migration step nahi chahiye.

# 6. Third-Party Integrations — Kaise Use Karenge

Chaaron integrations is version me CORE hain — build order priority ke hisab se: Exa pehle (sabse zyada features isi par depend karte hain), phir ElevenLabs aur Wispr Flow (dono independent aur fast to add), aur Render deployment ko timeline me hi ek dedicated slot diya gaya hai (Section 11 dekho) taaki last-minute scramble na ho.

## 6.1 Exa — AI Search Engine (build first)

- Job Search: user ke preferred job title se Exa API ke through real job postings (LinkedIn, Indeed, company pages) semantically search kiye jaayenge — ek hi call se listing ke liye zaroori fields (title, company, snippet) aur detail ke liye zaroori fields (full description, link) dono le lo.

- Career Path: job title se ‘career roadmap for <job title>’ / ‘skills required to become <job title>’ jaisi query Exa ko bhejo, top results se stages/skills extract karke structured JSON banao (detail Section 9 me).

- Research Links: har top missing skill ke liye Exa se best matching documentation, courses aur tutorials fetch honge.

- Backend Usage: ek simple ExaService function/class banayenge (Python) jo teeno jagah (job search, career path, research links) reuse ho — extra abstraction me time waste mat karo.

## 6.2 ElevenLabs — Voice Narration (core)

- Use Case: Career roadmap (aur chaho to job description) ko natural voice me sunane ka feature.

- Implementation: Backend endpoint /api/voice/narrate roadmap text leke ElevenLabs API ko call karega aur audio (base64 ya streamed URL) return karega; frontend me ek simple <audio> player / Play button. Isko chhota aur simple rakho — ek text field, ek button, ek audio tag, bas.

## 6.3 Wispr Flow — Voice Input (core)

- Use Case: User job title ko type karne ki jagah bol kar dictate kar sake.

- Implementation: Yeh OS/app-level dictation tool hai — seedha standard <input> field me kaam karega, koi backend code nahi chahiye. Sirf ensure karo ki job-title input ek normal, focusable text field ho jaha Wispr Flow inject ho sake — zero engineering risk, bas UI me thoda hint/icon daal do.

## 6.4 Render — Hosting & Deployment (core, timeline me dedicated slot)

- Frontend: React build ko Render Static Site ke roop me deploy karo (build: npm run build, publish dir: dist).

- Backend: FastAPI app ko Render Web Service (Python) par deploy karo (start: uvicorn main:app --host 0.0.0.0 --port $PORT).

- Environment Variables: EXA_API_KEY aur ELEVENLABS_API_KEY dono services ke Render Environment tab me daalo — kabhi Git me commit mat karo.

- CORS: Backend me frontend ka Render URL whitelist karna mat bhoolna, warna deployed frontend backend se baat nahi kar payega.

- Risk Mitigation: Deployment Section 11 ke timeline me 3:00–3:25 slot me hai — last 5 minute ka kaam nahi hai. Agar deploy fail ho jaye, local demo backup ready rakho (Section 12).

# 7. Simplified System Architecture

## 7.1 High-Level Architecture (stateless, no DB)

React (Frontend, deployed on Render Static Site)

↓  REST API calls (Axios, JSON)

FastAPI Backend (Python, deployed on Render Web Service)

↓                          ↓

Exa API                    ElevenLabs API

(job search / career path / research)    (voice narration)

No database layer — backend reads request data, calls Exa/ElevenLabs, returns response. Frontend holds resume/job/gap/roadmap data in React state for the session. Wispr Flow works at the browser/OS level directly on frontend input fields — it doesn't touch this diagram.

## 7.2 Frontend – Backend Integration Strategy

- Frontend React app sirf REST API calls karega — koi business logic frontend me nahi hogi.

- Ek central axios instance (api.js); local dev me base URL http://localhost:8000, deploy ke baad Render backend URL se .env replace karo.

- Backend FastAPI CORS middleware enable karega taaki React dev server aur deployed Render frontend URL dono se requests aa sake.

- Har baad ki API call (job search, gap analysis, career path) me pichla data (jaise resume skills) request body me hi bhej diya jaayega — backend kuch store nahi karega.

- API contract simple Pydantic models se define hoga; Swagger docs (/docs) se dono backend members aur frontend member isko live reference karenge.

## 7.3 Simplified API Endpoints (no auth, no DB)

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /api/resume/parse | Resume upload → extract skills/experience, return JSON (no storage) |
| GET | /api/jobs/search?title= | Exa se jobs search — returns listing + full detail together |
| POST | /api/skills/gap-analysis | Resume skills + job description (dono body me bhejo) → missing skills |
| GET | /api/career-path?title= | Exa se live career-path roadmap search + parse (Section 9) |
| POST | /api/career-path/customize | Roadmap + tech preference → Exa re-query → personalized steps |
| GET | /api/resources/search?skill= | Exa se missing skill ke liye research links |
| POST | /api/voice/narrate | Roadmap text → ElevenLabs audio (core) |

# 8. Team Structure & Responsibilities

Team 4 members ki hai. Auth na hone ki wajah se dono backend members poora focus core AI logic + integrations par de sakte hain:

| Member | Role | Responsibilities |
| --- | --- | --- |
| You (Team Lead) | Backend Developer | Resume upload & parsing endpoint (/api/resume/parse), skill-gap analysis endpoint, Render backend deployment, integration glue. |
| Member 2 | Frontend Developer | Poora React UI in one flow — resume upload, job listing, job detail, skill gap, career-path + audio-player screens; Wispr Flow-ready input field; Render frontend deployment; API integration (Axios). |
| Member 3 | Backend Developer | Exa API integration (job search + career-path search/parse + research links), ElevenLabs narration endpoint. |
| Member 4 | QA / Testing & Support | 0–30 min: help finalize API contract + test Exa/ElevenLabs API responses in Postman. After that: test every feature as it's built, fix small bugs, verify Render deployment end-to-end. |

## 8.1 How the 2 Backend Members Split Work

Backend ko do clear, independent modules me divide karo taaki dono members ek doosre ko block na karein:

- You — ‘Resume & Matching’ Module: Resume parsing endpoint aur skill-gap analysis endpoint (in dono ka input/output simple hai — text in, JSON out).

- Member 3 — ‘Jobs, Career & Voice’ Module: Exa job search, Exa career-path search + parsing, research links, ElevenLabs narration endpoint (yeh sab external-API-heavy, largely independent).

Dono modules alag Python files (e.g. routes_resume.py vs routes_jobs.py) me rahenge — merge conflicts practically zero honge, aur end me sirf main.py me dono routers include karne hain.

# 9. Career Path — Exa-Driven Generation Strategy

Career path Exa API se dynamically generate hoga (koi hardcoded template nahi). Isse roadmap kisi bhi job title ke liye kaam karega, real/current info ke saath — lekin time-box tight rakhna zaroori hai.

## 9.1 How It Works

- Job title milte hi backend Exa ko query bhejta hai: ‘career roadmap to become <job title>’ / ‘skills required for <job title> step by step’.

- Exa top 3–5 results (articles/guides) return karega — unke content/summary se backend ek simple parsing logic (keyword/heading based split) se stages banayega: Beginner → Intermediate → Advanced.

- Agar parsing clean structure na de paye, ek lightweight rule apply karo: results ke top skills/keywords ko frequency ke hisab se 3 buckets me baant do — yeh ‘good enough’ hai demo ke liye, perfect nahi hona chahiye.

- User tech preference dene ke baad, ek doosra targeted Exa query jaata hai: ‘<technology> roadmap for <job title>’, jiske results se relevant stage ko refine/replace kiya jaata hai.

## 9.2 Skill-Gap Highlighting

- Missing skills list (skill-gap endpoint se aayi) ko roadmap ke stages ke saath simple keyword match karo — jahan match mile, us stage me highlight kar do.

- Top 2–3 highlighted missing skills ke liye Exa se research links fetch honge (sab ke liye nahi, taaki API calls slow na ho).

## 9.3 Speed & Reliability Tips (important given the time-box)

- Exa response ko turant frontend ko forward karo, backend me heavy NLP/summarization mat karo — simple string operations (split, keyword count) hi kaafi hain.

- Response timeout set karo (e.g. 8–10 sec) — agar Exa slow ho, ek generic 3-stage fallback text (‘Beginner: fundamentals, Intermediate: tools & projects, Advanced: specialization’) turant dikha do taaki UI kabhi blank/frozen na dikhe.

- Career-path aur customize dono endpoints ko demo se pehle 2–3 baar alag job titles ke saath test kar lo, taaki pata ho response kaisa aata hai.

# 10. Fast Git Workflow (Hackathon Mode)

4 hours me heavy-weight PR process time-waste hai. Speed-first, lightweight workflow follow karo — lekin thoda structure zaroori hai taaki last-minute merge conflicts na ho.

## 10.1 Branch Structure (minimal)

| Branch | Owner | Purpose |
| --- | --- | --- |
| main | Team Lead (You) | Yeh hi demo/deployed version hoga. Sirf tested, working code yahan aaye. |
| resume-parser | You | Resume upload & parsing endpoint. |
| skill-gap | You | Skill gap analysis logic. |
| frontend | Member 2 | Poora React app — saari screens ek hi branch me (time bachane ke liye alag-alag branches mat banao). |
| job-search | Member 3 | Exa API job search integration. |
| career-path-voice | Member 3 | Exa career-path search/parse + research links + ElevenLabs narration endpoint. |
| deploy | You (with Member 4) | Render config files (e.g. render.yaml), env var setup, final deployment checks. |

## 10.2 Workflow

- Shuru me hi repo bana lo, sabko add karo, apni-apni branch banao (git checkout -b branch-name).

- Har 20–30 min me apni branch push karo — chhote commits, koi lambi delay nahi (‘commit early, commit often’).

- Formal PR review skip karo — bas ek quick message team group me: ‘pushed X, please pull & check’.

- Har 1 hour me sab log apni branch ko main me merge karo (ya ek shared ‘integration’ branch me) taaki conflicts jaldi pakde jayein, bade merge ke intezar me nahi.

- Merge tum (Team Lead) karo taaki main hamesha working state me rahe.

- Agar conflict aaye, jisne last change kiya wahi turant resolve kare — mat delay karo dusre ka kaam.

## 10.3 Commit Message (short, no need for strict convention)

- feat: resume parsing endpoint

- fix: job card click bug

- wip: career path (in progress) — in-progress commits bhi theek hain, hackathon me perfection zaroori nahi.

## 10.4 .env / Secrets

- .env file me EXA_API_KEY (aur agar use ho to ELEVENLABS_API_KEY) rakho, .gitignore me daal do — keys kabhi commit mat karo, chahe hackathon hi kyun na ho.

# 11. 4-Hour Timeline

| Time | Focus | Deliverables |
| --- | --- | --- |
| 0:00–0:20 | Setup | Repo + boilerplate (React app, FastAPI app), API contract (JSON shapes) decide together, Exa + ElevenLabs API keys test, branches banao. |
| 0:20–1:15 | Backend Core | You: resume parsing + skill-gap endpoints. Member 3: Exa job-search endpoint working + first Exa career-path query working. |
| 1:15–2:15 | Parallel Build | Member 3: career-path parsing/stages logic + tech-customize endpoint + ElevenLabs narration endpoint. Member 2: frontend screens ban rahi hain mock data ke saath, Wispr Flow-ready input field, audio-player component. You: help wherever blocked + start Render backend config. |
| 2:15–2:55 | Integration | Frontend ko real backend endpoints se jodo, ek-ek karke test karo (upload → search → gap → career path → voice). |
| 2:55–3:25 | Render Deployment | Backend Web Service + Frontend Static Site deploy karo, env vars set karo, CORS fix karo, deployed link se end-to-end test karo. |
| 3:25–3:50 | Bug Fix + Polish | Jo bhi bug mile (local ya deployed) turant fix, thoda UI polish. |
| 3:50–4:00 | Demo Run-through | Poora flow deployed link par ek baar chalao exactly jaise judges ke saamne dikhaoge, backup screenshots/video le lo. |

Tip: Member 2 (frontend) ko backend endpoints ka wait nahi karna chahiye — API contract Step 1 me hi fix ho jaana chahiye, phir frontend mock/dummy JSON se shuru se hi build ho sakta hai aur baad me sirf mock data ko real API se swap karna hai.

Yeh timeline tight hai kyunki 4 integrations core hain — agar 1:15 tak Exa career-path query working na ho, turant fallback (Section 9.3) pe switch karo aur aage badho, wapis debug karne me time mat lagao.

# 12. Demo & Stretch Goals

## 12.1 Safe Demo Setup

- Primary: Render deployed link (both frontend + backend) — yeh isliye timeline me hi allocate kiya gaya hai.

- Backup: agar deployed link me last-minute issue aaye, local par run karke (React localhost:5173 + FastAPI localhost:8000) screen-share se demo do.

- Venue ka wifi pehle test kar lo — Exa aur ElevenLabs dono live internet API calls hain.

- Har API call ka ek pehle se successful run ka screen-recording/screenshots ready rakho, in case live demo me koi call slow/fail ho jaye.

## 12.2 True Stretch Goals (only if everything above is done with time left)

- Downloadable PDF of the career roadmap.

- UI polish — loading states, subtle animations, better audio-player styling.

- Job listing par thoda filter/sort add karna (agar Exa results me multiple jobs aa rahe hain).